## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Automated student credit center automation system | suzan hazourri | 2022-06-02 | 2022-08-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Getting a loan |  | suzan |  | 2020-06-03 | 2020-06-15 | 12 | Complete
| Interface to enter the user name and information about it | Interface | Batoul M Ali |  | 2020-06-03 | 2020-06-07 | 4 | Complete
| Building a database and adding students to it | Access to the database | Doha |  | 2020-06-07 | 2020-06-15 | 8 | Complete
| Pay off the loan |  | Batol Rashed |  | 2020-06-18 | 2020-07-08 | 20 | In Progress
| enter the student number to access his database | Access to the database | Batoul M Ali |  | 2020-06-18 | 2020-06-24 | 6 | In Progress
| An interface contains options for specifying the type of loan and a text for entering the amount to be repaid | Interface | Batol Rashed |  | 2020-06-24 | 2020-06-30 | 6 | Not Started
| Calculating interest to be paid |  | suzan |  | 2020-06-30 | 2020-07-03 | 3 | Not Started
| Deduction of the amount paid from the database |  | Doha |  | 2020-07-03 | 2020-07-05 | 2 | Not Started
| Design the shape of the jumper to be printed | design | Doha |  | 2020-07-05 | 2020-07-08 | 3 | Not Started
| Inquiry about the amount paid out |  | batuol m ali |  | 2022-07-08 | 2022-07-18 | 10 | Not Started
| Building an interface to enter the student number | Interface | suzan |  | 2022-07-08 | 2022-07-12 | 4 | Not Started
| Access to the database and print the amount to be paid | Access to the database | Batol Rashed |  | 2022-07-12 | 2022-07-18 | 6 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.